## FHI Full Document Checklist
This Checklist details the documents that must be submitted to comply with the FHI Program. The documents required to be submitted for Milestone encompasses all documents previously required to be submitted.
Document | Kickoff Meeting | Design Phase | Closing | Milestone #1 | Construction Kickoff Meeting | Milestone #2 Rough In | Milestone #3 Substantial Completion | Milestone #4 Completion
Project Acceptance
Participation Agreement - Signed | X
W-9 - Signed | X
Passive House Consultant Contract - Signed | X
Project Team and Roles | X |  |  |  | X
Budget Worksheet
Budget Worksheet at FHI Application | X
Budget Worksheet at Closing |  |  | X
Budget Worksheet at Project Completion | [7 empty] | X
Design and Construction Documents
Design Documents to Initiate FHI Design Review Process | X
50% - 100% Construction Documents (drawings and specifications) with FHI requirements incorporated |  | X | X
Completed FHI Design Review |  |  | X
100% Construction Documents (associated with GC contract) |  |  |  | X
Passive House Certification
Passive House Registration Confirmation |  | X
Passive House Precertification Approval |  |  |  | X
Passive House Energy Modeling Report 1 |  |  | X
Passive House Certifier Review 1 |  |  | X
Passive House Energy Model |  |  |  | X |  |  |  | X
Passive House Construction Phase QC/QA Reports (e.g. Phius Multifamily Quality Assurance Workbook) | [6 empty] | X
Passive House Certification Approval | [7 empty] | X
1 if pre-certification is not achieved before closing
Closing Documents
Construction Contract (draft is acceptable pre-closing) |  |  | X | X
FHI Rider - Signed |  |  | X
HPD Commitment Letter |  |  | X
Construction Administration Plan
Construction Team Project Champion |  |  |  |  | X
Construction Schedule with Passive House and FHI Testing and Commissioning Requirements Incorporated |  |  |  |  | X
Contractor and Team Member Passive House Training Verification |  |  |  |  | X
Construction
Inspection Report(s) - Air/Thermal Boundary2 | [5 empty] | X | X
Inspection Report(s) - Space Conditioning HPs2 | [5 empty] | X | X
Inspection Report(s) - DHW HPs2 | [5 empty] | X | X
Inspection Report(s) - Ventilation System2 | [5 empty] | X | X
Refrigerant Charging Reports (if applicable) | [5 empty] | X | X
Room Heat Pump Air Leakage Test Report (if applicable) | [5 empty] | X
Whole Building Air Leakage Test Report | [6 empty] | X
Testing, Adjusting, Balancing Report | [6 empty] | X
Space Conditioning Heat Pump Testing Report as per FHI Technical Requirements | [6 empty] | X
Space Conditioning Heat Pump Commissioning Report | [6 empty] | X
Domestic Hot Water System Commissioning Report | [6 empty] | X
Latest Approved AIA G702/G703 |  |  |  |  | X | X | X
2 provided by Passive House Verifier and/or TAP inspection
Project Completion
Operation and Maintenance Documentation on HVAC and DHW Systems | [7 empty] | X
Operation and Maintenance Training on HVAC and DHW Systems | [7 empty] | X
Maintenance Contract for HVAC & DHW Systems (if applicable) | [7 empty] | X
Manufacturer and Contractor Warranties on Equipment and Labor as per FHI Requirements | [7 empty] | X
Resident Manual with Relevant FHI and Passive House Information Included | [7 empty] | X
NYSERDA Data Release Authorization Forms (if required) | [7 empty] | X
As-Built Drawings | [7 empty] | X
Passive House Final Certification | [7 empty] | X
Final G702/G703 | [7 empty] | X

## Milestone 1
Document | Milestone #1 | Submitted | Notes
Project Acceptance
Participation Agreement - Signed | X
W-9 - Signed | X
Passive House Consultant Contract - Signed | X
Project Team and Roles | X
Budget Worksheet
Budget Worksheet at FHI Application | X
Budget Worksheet at Closing | X
Design and Construction Documents
Design Documents to Initiate FHI Design Review Process | X
50% - 100% Construction Documents (drawings and specifications) with FHI requirements incorporated | X
Completed FHI Design Review | X
100% Construction Documents (associated with GC contract) | X
Passive House Certification
Passive House Registration Confirmation | X
Passive House Precertification Approval | X
Passive House Energy Modeling Report 1 | X
Passive House Certifier Review 1 | X
Passive House Energy Model | X
1 if pre-certification is not achieved before closing
Closing Documents
Construction Contract (draft is acceptable pre-closing) | X
FHI Rider - Signed | X
HPD Commitment Letter | X

## Milestone 2
Document | Milestone #2 Rough In | Submitted | Notes
Project Acceptance
Project Team and Roles | X
Construction Administration Plan
Construction Team Project Champion | X
Construction Schedule with Passive House and FHI Testing and Commissioning Requirements Incorporated | X
Contractor and Team Member Passive House Training Verification | X
Construction
Inspection Report(s) - Air/Thermal Boundary2 | X
Inspection Report(s) - Space Conditioning HPs2 | X
Inspection Report(s) - DHW HPs2 | X
Inspection Report(s) - Ventilation System2 | X
Refrigerant Charging Reports (if applicable) | X
Room Heat Pump Air Leakage Test Report (if applicable) | X
Latest Approved AIA G702/G703 | X
2 provided by Passive House Verifier and/or TAP inspection

## Milestone 3
Document | Milestone #3 Substantial Completion | Submitted | Notes
Passive House Certification
Passive House Construction Phase QC/QA Reports (e.g. Phius Multifamily Quality Assurance Workbook) | X
Construction
Inspection Report(s) - Air/Thermal Boundary2 | X
Inspection Report(s) - Space Conditioning HPs2 | X
Inspection Report(s) - DHW HPs2 | X
Inspection Report(s) - Ventilation System2 | X
Refrigerant Charging Reports (if applicable) | X
Whole Building Air Leakage Test Report | X
ERV Testing, Adjusting, Balancing Report | X
Space Conditioning Heat Pump Testing Report as per FHI Technical Requirements | X
Space Conditioning Heat Pump Commissioning Report | X
Domestic Hot Water System Commissioning Report | X
Latest Approved AIA G702/G703 | X
2 provided by Passive House Verifier and/or TAP inspection

## Milestone 4
Document | Milestone #4 Completion | Submitted | Notes
Budget Worksheet
Budget Worksheet at Project Completion | X
Passive House Certification
Passive House Energy Model | X
Passive House Certification Approval | X
1 if pre-certification is not achieved before closing
Project Completion
Operation and Maintenance Documentation on HVAC and DHW Systems | X
Operation and Maintenance Training on HVAC and DHW Systems | X
Maintenance Contract for HVAC & DHW Systems (if applicable) | X
Manufacturer and Contractor Warranties on Equipment and Labor as per FHI Requirements | X
Resident Manual with Relevant FHI and Passive House Information Included | X
NYSERDA Data Release Authorization Forms (if required) | X
As-Built Drawings | X
Passive House Final Certification | X
Final G702/G703 | X