## Closing Checklist
FUTURE HOUSING INITIATIVE: PRE-CLOSING CHECKLIST FOR PARTICIPANTS (Steps & Documents required to receive the NYSERDA Final Incentive Award Letter)
Project:
Recipient: Project Team including Owner/Sponsor, Architect/Engineer, HPD Project Manager
Initiating Party | UPON PRELIMINARY ACCEPTANCE | Responsible Recipient: | Received: | Comments:
Owner Team | Participation Agreement - signed by Owner Team | HPD
HPD | Project Team and Roles | Owner Team, HPD, TAP
Owner Team | Passive House Consultant Contract - Signed | HPD, TAP
Owner Team | W-9 - signed | HPD
Owner Team | Budget Worksheet - FHI Application | HPD, NYSERDA
Owner Team | Current Design/Construction Documents | HPD, TAP
Initiating Party | POST ACCEPTANCE/DESIGN REVIEW PHASE | Responsible Recipient: | Received: | Comments:
Owner Team | Passive House Project Registration Confirmation | TAP
Owner Team | Construction Documents with Passive House and FHI design updates. | TAP
TAP | Design Review(s) by TAP | Owner Team
Initiating Party | IN PREPARATION FOR BIDDING/PRICING - 5-8 weeks before closing | Responsible Recipient: | Received: | Comments:
Owner Team | Construction Documents and Specs for Bid including all Passive House and FHI requirements and addressing all outstanding TAP comments issued via the Design Review Checklist. | TAP
Owner Team | Passive House Pre-Certification Approval Letter | TAP
Owner Team | Passive House Energy Modeling Report (if not yet Pre-certified) | TAP
Owner Team | Passive House Certifier Review (if not yet Pre-certified) | TAP
TAP | TAP reviews final Construction Documents & confirms program requirements are met. TAP approves final design for Closing (this is a requirement for the next phase). | NYSERDA
Initiating Party | AT LEAST 4 WEEKS PRIOR TO CLOSING - The following documents must be received by TAP. Once received, it will take 3-4 weeks to generate the signed Final Incentive Award Letter from NYSERDA. | Responsible Recipient: | Received: | Comments:
Owner Team | Executed Construction Contract (draft is acceptable; executed version to be submitted when available) | HPD
Owner Team | Completed FHI Rider signed by Owner Team and Contractor | HPD
Owner Team | Construction Schedule (draft is acceptable; final version to be submitted when available) | HPD
HPD | HPD Commitment Letter to abide by Construction Schedule (draft is acceptable; executed version to be submitted when available) | Owner Team/NYSERDA
Owner Team | Budget Worksheet for Closing | HPD/NYSERDA
Owner Team | Construction Documents & Specs including any Addendum from Bidding | TAP
Initiating Party | PRIOR TO CLOSING - NYSERDA releases the signed Final Incentive Award Letter contingent on receiving all documents above | Responsible Recipient: | Received: | Comments:
TAP | NYSERDA releases the signed Final Incentive Award Letter. Note: this letter cannot be signed until all documents above are submitted. | Owner Team
Post Closing: See FHI Full Document Checklist